## Contract 7
NOTE: THE USE OF THIS SPREADSHEET IS AT YOUR OWN RISK. IT IS THE RESPONSIBILITY OF EACH AND EVERY INDIVIDUAL OR TENDERER TO ENSURE THAT THE QUANTITIES ARE AS PER THE BILL OF QUANTITIES ISSUED AND THAT THE CALCULATIONS ARE CORRECT. THE CLIENT ACCEPTS NO RESPONIBILITY OF THE USE OF THIS SPREADSHEET
ITEM | PAYMENT REFERS | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
| SANS 1200 A | SCHEDULE 1: PRELIMINARY AND GENERAL |  |  |  |  | Duration = | 10 | months
| 8.3 | FIXED-CHARGE AND VALUE-RELATED ITEMS
1.1 | 8.3.1 | Contractual Requirements | Sum | 1
| 8.3.2 | Establish facilities on the Site
1.2 | 8.3.2.3 | Facilities for Engineer:
1.2.1 | PSAB 3.2 | (a) Furnished offices (1 No.) | Sum | 1
1.2.2 |  | (b) Telephone | Sum | 1
1.2.3 |  | (c) Nameboard (1 No.) | Sum | 1
1.2.4 |  | (d) Provision of survey equipment | Sum | 1
1.2.5 |  | (e) Engineers Equipment: G15 5530 15.6-inch Core i7-13650HX 16GB RAM 1TB SSD GeForce RTX 4060 Win 11 Pro Laptop with Microsoft 365 Business Standard 1-Year Subscription. | Sum | 1
1.3 |  | Facilities for Contractor for duration of construction except where otherwise stated
1.3.1 |  | (a) Offices, workshops and storage sheds | Sum | 1
1.3.2 |  | (b) Ablution and latrine facilities | Sum | 1
1.3.3 |  | (c) Laboratories | Sum | 1
1.3.4 |  | (d) Living Accomodation | Sum | 1
1.3.5 |  | (e) Tools and equipment | Sum | 1
1.3.6 |  | (f) Water supplies, electric power and communications | Sum | 1
1.3.7 |  | (g) Refuse bins at the site camp | Sum | 1
1.3.8 |  | (h) Dealing with water (Subclause 5.5) | Sum | 1
1.3.9 |  | (i) Access (see 5.8) | Sum | 1
1.3.10 |  | (j) Plant | Sum | 1
1.4 | 8.3.3 | Other Fixed-Charge Obligations | Sum | 1
1.5 | 8.3.4 | Removal of Engineer's and Contractor's site establishment on completion | Sum | 1
1.6 | PSA 8.4.6 | Compliance with Occupational Health & Safety. The sum shall cover the fixed cost associated with the Contractor's Health & Safety Obligations | Sum | 1
1.7 | PSHSS 6.1.2; CR 5(1)(l) | i) Preparation of the Contractor's site specific Health and Safety Plan | Sum | 1
1.8 | CR 7(1)(b) | ii) Principal Contractor's initial obligations in respect of the Occupational Health and Safety Act and Construction Regulations | Sum | 1
1.9 | CR 7(1)(g) | iii) Cost of medical certificates and medical surveillance
1.9.1 | PSHSS 7.2 | (a) Initial (baseline) medical examinations | No | 20
1.9.2 |  | (b) Exit medical examinations | No | 20
1.9.3 |  | iv) Allowance for Health and Safety Officer | Sum | 1
TOTAL CARRIED FORWARD
BROUGHT FORWARD
1.1 | GSR 2; PSHSS 7.7 | v) Provision of EPWP Branded SABS Personal Protective Equipment
1.10.1 |  | (a) Hard Hats | No | 20
1.10.2 |  | (b) Reflective vests | No | 20
1.10.3 |  | (c) Protective foot wear | Pair | 20
1.10.4 |  | (d) Dust masks FFP2 | No | 20
1.10.5 |  | (e) Gloves | Pair | 20
1.11 | PSA 8.4.7 | Compliance with Environmental Management Obligations. The sum shall cover the fixed cost associated with the Contractor's Environmental Management Obligations | Sum | 1
1.12 |  | Compliance with As-Built Requirements | Sum | 1
| 8.4 | SCHEDULED TIME-RELATED ITEMS
1.13 | 8.4.1 | Contractual Requirements | Sum | 1
| 8.4.2 | Operation and Maintenance of Facilities on Site, for Duration of Construction, except where otherwise stated for engineer
1.14 | 8.4.2.1 | Facilities for the Engineer:
1.14.1 |  | (a) Furnished Office | Sum | 1
1.14.2 |  | (c) Nameboard (1 No.) | Sum | 1
1.15 | 8.4.2.2 | Facilities for Contractor:
1.15.1 |  | (a) Offices, workshops and storage sheds | Sum | 1
1.15.2 | PS 7.2 | (b) Ablution and latrine facilities | Sum | 1
1.15.3 | PS 7.6 | (c) Living Accomodation | Sum | 1
1.15.4 |  | (d) Tools and equipment | Sum | 1
1.15.5 | PS 7.1 | (e) Water supplies, electric power and communications | Sum | 1
1.15.6 |  | (f) Dealing with water (Subclause 5.5) | Sum | 1
1.15.7 |  | (g) Access (see 5.8) | Sum | 1
1.15.8 |  | (h) Plant | Sum | 1
1.16 | 8.4.3 | Supervision for the Duration of Construction | Sum | 1
1.17 | 8.4.5 | Other Time-Related Obligations: | Sum | 1
1.18 | PD | Compliance with Occupational Health & Safety. The sum shall cover the fixed cost associated with the Contractor's Health & Safety Obligations | Sum | 1
1.19 | PE | Compliance with Environmental Management Obligations. The sum shall cover the fixed cost associated with the Contractor's Environmental Management Obligations | Sum | 1
TOTAL CARRIED FORWARD
BROUGHT FORWARD
1.2 | PSA 8.4.6.2 | Security Services Costs | Month | 10
1.21 | 8.3.7 | Compliance with As-Built Requirements | Sum | 1
1.22 |  | External full-time SACPCMP registered Construction Health and Safety Officer supervision for the duration of the contract | Prov. Sum | 1 | 200000 | 200000
1.23 |  | Overheads, charges & profit on above provisional sum | % | 200000
1.24 |  | Allowance for Social Facilitation (ISD) services for the duration of the contract | Prov. Sum | 1 | 250000 | 250000
1.25 |  | Overheads, charges & profit on above provisional sum | % | 250000
1.26 |  | Allowance for ECO for the duration of the contract | Prov. Sum | 1 | 200000 | 200000
1.27 |  | Overheads, charges & profit on above provisional sum | % | 200000
1.28 |  | Sums stated provisionally by Engineer:
1.28.1 | PS12 | Employment of CLO for the duration of the Contract (R8500 pm plus R500 pm cellphone allowance) | Prov. Sum | 1 | 90000 | 90000
1.28.2 |  | Overheads, charges & profit on above provisional sum | % | 90000
1.28.3 |  | Reimbursement / Payment of PSC members for attendance of meetings for the duration of the contract (5 No members at R500 per member per meeting) | Prov. Sum | 1 | 25000 | 25000
1.28.4 |  | Overheads, charges & profit on above provisional sum | % | 25000
1.28.5 |  | Allow for Civil Engineering, Environmental and Health & Safety trainee student (3 No of Young Graduates) | Prov. Sum | 1 | 285000 | 285000
1.28.6 |  | Overheads, charges & profit on above provisional sum | % | 285000
1.28.7 |  | Telephone for Employers Agent & Assistant | Prov. Sum | 1 | 20000 | 20000
1.28.8 |  | Overheads, charges & profit on above provisional sum | % | 20000
1.28.9 |  | Allow for Additional Construction Monitoring - Level 3 for the full duration of the contract | Prov. Sum | 1 | 400000 | 400000
1.28.10 |  | Overheads, charges & profit on above provisional sum | % | 400000
1.28.11 |  | Allow for the provision of the Engineer's Bakkie for the duration of the Contract. The amount allowed for is inclusive of fuel | Prov. Sum | 1 | 144000 | 144000
1.28.12 |  | Overheads, charges & profit on above provisional sum | % | 144000
1.28.13 |  | Employer's Agent cost for Environmental Management Plan, Method Statement and Contractor Training | Prov. Sum | 1 | 80000 | 80000
1.28.14 |  | Overheads, charges & profit on above provisional sum | % | 80000
1.28.15 |  | Allow provisional sum for the specialised testing of the works, either material or completed works as instructed by the Employers Agent | Prov. Sum | 1 | 30000 | 30000
1.28.16 |  | Overheads, charges & profit on above provisional sum | % | 30000
1.28.17 |  | Allow provisional sum for the accredited training of selected potential local labourers | Prov. Sum | 1 | 120000 | 120000
1.28.18 |  | Overheads, charges & profit on above provisional sum | % | 120000
TOTAL CARRIED FORWARD
BROUGHT FORWARD
1.28.19 |  | Allow provisional sum for the non-accredited training of selected potential local labourers | Prov. Sum | 1 | 50000 | 50000
1.28.20 |  | Overheads, charges & profit on above provisional sum | % | 50000
| 8.7 | Dayworks (Provisional)
1.29 | PSA8-5 | a) Labour
1.29.1 |  | i) Foreman | hrs | 50
1.29.2 |  | ii) Skilled | hrs | 50
1.29.3 |  | iii) Semi-skilled | hrs | 50
1.29.4 |  | iv) Unskilled | hrs | 50
1.3 |  | b) Plant
1.30.1 |  | i) 6m³ Tip Truck | hrs | 50
1.30.2 |  | ii) 10m³ Tip Truck | hrs | 50
1.30.3 |  | iii) Tractor-Loader-Backhoe | hrs | 30
1.30.4 |  | iv) Compactors (Wacker or similar approved) | hrs | 30
1.31 |  | c) Materials
1.31.1 |  | i) Allow for net cost of goods or materials actually used | Prov. Sum | 1 | 50000 | 50000
1.31.2 |  | ii) Overheads, charges & profit on above provisional sum | % | 50000
1.32 |  | Temporary Works
1.32.1 |  | (a) Verification and protection of existing services | Sum | 1
TOTAL OF SCHEDULE 1 CARRIED FORWARD TO SUMMARY
| SANS 1200 C | SCHEDULE 2: SITE CLEARANCE
2.1 |  | Clear Site
2.1.1 | 8.2.1 | Clear and grub for pipeline routes up to a width of 2m. | m | 51975
2.1.2 | 8.2.2 | Remove and grub large trees and tree stumps of girth:
2.1.3 |  | a) Over 1.0m and up to 2.0m | No. | 0 |  | Rate Only
2.1.4 | PSC1 | Remove topsoil in 600mm wide strip to depth of 150mm, stockpile, maintain and reinstate. | m³ | 3776.3
| 8.2.5 | Take down existing fences:
2.2 | PSC3 | Remove and/or secure existing fences that intersect a trench
2.2.1 |  | Diamond mesh fencing up to 2m high | m |  |  | Rate Only
2.3 | PSC3 | Remove and secure existing fences that adjoin a trench
2.3.1 |  | Diamond mesh fencing up to 2m high | m |  |  | Rate Only
2.4 | PSC 8.2.13 | Remove existing gravel layer works to stockpile and maintain (for use as selected layers) as instructed by the Engineer.
2.4.1 |  | Gravel layer works to District Roads. | m³ | 554.4
2.4.2 |  | Fill material | m³ | 74.8
2.5 |  | MISCELLANEOUS
2.5.1 |  | Diversion berm, to detail, across road inclusive of imported gravel, compaction and shaping | m³ | 15
2.5.2 |  | Ungrouted stone pitching, to detail, to from shallow ditch drain at berm outlet | m² | 20
2.5.3 |  | Construct concrete V-drain, to detail, inclusive of excavation and re-inforcement | m² | 0 |  | Rate Only
TOTAL OF SCHEDULE 2 CARRIED FORWARD TO SUMMARY
| SABS 1200 DB | SCHEDULE 3: EARTHWORKS (PIPE TRENCHES)
Excavation (Provisional)
3.1 | 8.3.2(a) | Excavate in all materials for trenches backfill, compact, and dispose of surplus/unsuitable material, for pipes up to 400mm dia for total trench depth: (ref. PSDB1, PSDB2, PSDB3 and PSDB5)
3.1.1 |  | 0.0 m to 1.5 m | m³ | 62370
3.1.2 |  | 1.5 m to 3.5 m | m³ | 26.236
3.2 | 8.3.2(b) | Extra over items C.1.1 for excavation (provisional) in: (ref. PSDB3)
3.2.1 |  | Hard Rock Material | m³ | 1449.9
3.2.2 |  | Boulder excavation, class A | m³ |  |  | Rate Only
3.2.3 | 8.3.2(c) | Excavate unsuitable material from bottom of trench, incl. backfill compact and dispose of surplus material within freehaul distance of 1 km (Ref PSDB4) | m³ | 2319.84
3.3 | 8.3.3 | Excavation ancillaries
3.3.1 | 8.3.3.1 (c) | Make up deficiency in backfill material, by importation from borrow pit selected by Contractor | m³ | 5218.6
3.4 | 8.3.3.3 | Compaction in road reserves (ref. PSDB 3.5)
3.4.1 |  | Compact with material from commercial source to 95% Mod AASHTO | m³ | 1565.6
3.4.2 | PSDB1 | Backfilling trenches using 13mm washed stone | m³ |  |  | Rate Only
3.4.3 | 8.3.3.4 | Extra-over Items 8.3.3.1 (c) for overhaul, in excess of freehaul distance of 1 km | m³.km | 4435.81
| 8.3.5 | Existing Services that Intersect or Adjoin a Pipe Trench
3.5 |  | (a) Services that intersect a trench a pipe trench
3.5.1 |  | i) ESKOM cables | No. | 3
3.5.2 |  | iii) Watermains up to 300mm dia | No. |  |  | Rate Only
3.5.3 |  | (b) Services that adjoin a trench a pipe trench
3.5.4 |  | i) ESKOM cables | m | 6
3.5.5 |  | iii) Watermains up to 300mm dia | m | 5
TOTAL OF SCHEDULE 3 CARRIED FORWARD TO SUMMARY
| SABS 1200 L | SCHEDULE 4: MEDIUM-PRESSURE PIPELINES
4.1 | 8.2.1 | Supply, bed, lay, disinfect, join and test potable water pipelines on flexible bedding, complete with couplings. All works inclusive in the rate, except where specific items are provided. All activites in accordance with project specifications:
HDPE Pipes
4.1.1 |  | 50mm dia. HDPE Class PN 10 | m | 35380
4.1.2 |  | 63mm dia. HDPE Class PN 10 | m | 1590
4.1.3 |  | 75mm dia. HDPE Class PN 10 | m | 3080
PVC-U Pipes
4.1.4 |  | 90mm dia. uPVC Class 9 | m | 585
4.1.5 |  | 110mm dia. uPVC Class 9 | m | 2405
4.1.6 |  | 160mm dia. uPVC Class 9 | m | 5980
4.1.7 |  | 200mm dia. uPVC Class 9 | m | 1960
4.1.8 |  | 250mm dia. uPVC Class 9 | m | 995
4.3 | 8.2.2 | Anchor/thrust blocks and pedestals
4.3.1 |  | a) Concrete (15MPa/19) | m3 | 32
4.4 |  | Marker Posts
4.4.1 |  | Supply, paint and install precast concrete marker post as directed by the Engineer. Work to be executed by a nominated SMME sub contractor | No | 100
4.5 |  | Supply and install standpipe complete including HDPE saddle, 32mm HDPE pipe (20m), tap and galvanised riser pipe, concrete work including shuttering, elbows, nipples, etc, as per standard drawings. Work to be executed by a nominated SMME sub contractor | No | 200
4.6 |  | Install Aqua Flow limiters where instructed by the Engineer complete as per detailed drawings. Work to be executed by a nominated SMME sub contractor | No | 32
TOTAL OF SCHEDULE 4 CARRIED FORWARD TO SUMMARY
| SANS 1200 L | SCHEDULE 5: PIPE FITTINGS AND SPECIALS
| 8.2.2 PSL 8.2.4 PSL 8.2.5 | Extra-over 8.2.1 for the Supplying, Laying and Bedding of Specials complete with Couplings as follows:
| 8.2.4 PSL 8.2.6 | Supply, lay, joint and bed including cutting pipes where required for the following:
5.1 |  | uPVC Pipe Bends (Class 16)
5.1.1 |  | 90mm dia. x 11.25° bends. | No. | 5
5.1.2 |  | 90mm dia. x 22.5° bends. | No. | 1
5.1.3 |  | 110mm dia. x 11.25° bends. | No. | 17
5.1.4 |  | 110mm dia. x 22.5° bends. | No. | 6
5.1.5 |  | 110mm dia. x 45° bends. | No. | 1
5.1.6 |  | 160mm dia. x 11.25° bends. | No. | 21
5.1.7 |  | 160mm dia. x 11.25° bends. | No. | 1
5.1.8 |  | 160mm dia. x 45° bends. | No. | 1
5.1.9 |  | 200mm dia. x 11.25° bends. | No. | 2
5.1.10 |  | 250mm dia. x 11.25° bends. | No. | 5
5.1.11 |  | 250mm dia. x 22.5° bends. | No. | 2
5.1.12 |  | 250mm dia. x 45° bends. | No. | 2
5.1.13 |  | 250mm dia. x 90° bends. | No. | 1
HDPE Reducers
5.2 |  | HDPE PE100 reducer with a SDR of 11 and a pressure rating of 16 bar. The reducers must be suitable for butt welding on to PE100 HDPE pipe. All reducers must comply with SANS/ISO 4427
5.2.1 |  | 63mm x 50 mm | No. | 54
5.2.2 |  | 75mm x 50mm | No. | 7
5.2.3 |  | 75mm x 63mm | No. | 1
5.2.4 |  | 90mm x 50mm | No. | 3
5.2.5 |  | 90mm x 75mm | No. | 1
5.2.6 |  | 110mm x 63mm | No. | 13
5.2.7 |  | 110mm x 75mm | No. | 0 |  | Rate Only
5.2.8 |  | 140mm x 90mm | No. | 3
5.2.9 |  | 200mm x 140mm | No. | 3
5.3 |  | uPVC Reducers (Class 16)
5.3.1 |  | 110mm x 50mm | No. | 1
TOTAL CARRIED FORWARD
BROUGHT FORWARD
5.3.2 |  | 110mm x 75mm | No. |  |  | Rate Only
5.3.3 |  | 110mm x 90mm | No. | 2
5.3.4 |  | 160mm x 90mm | No. | 1
5.3.5 |  | 160mm x 110mm | No. | 4
5.3.6 |  | 200mm x 160mm | No. | 2
5.3.7 |  | 250mm x 200mm | No. | 3
5.4 |  | Equal Tees (PN16)
5.4.1 |  | 50mm x 50mm | No. | 28
5.4.2 |  | 75mm x 75mm | No. | 3
5.4.3 |  | 110mm x 110mm | No. | 1
5.4.4 |  | 160mm x 160mm | No. | 1
5.4.5 |  | 250mm x 250mm | No. | 1
5.5 |  | Reducing Tees (PN16)
5.5.1 |  | 63mm x 50 mm | No. | 1
5.5.2 |  | 75mm x 50mm | No. | 2
5.5.3 |  | 90mm x 63mm | No. | 1
5.5.4 |  | 90mm x 75mm | No. | 1
5.5.5 |  | 110mm x 63mm | No. | 10
5.5.6 |  | 110mm x 75mm | No. | 3
5.5.7 |  | 160mm x 63mm | No. | 27
5.5.8 |  | 160mm x 110mm | No. | 0 |  | Rate Only
5.5.9 |  | 200mm x 110mm | No. | 14
5.5.10 |  | 250mm x 200mm | No. | 3
5.6 |  | Cross
5.6.1 |  | 50mm x 50mm | No. | 1
5.6.2 |  | 63mm x 63mm | No. | 1
5.6.3 |  | 160mm x 50mm | No. | 1
5.6.4 |  | 160mm x 75mm | No. | 1
5.6.5 |  | 250mm x 50mm | No. | 1
5.7 |  | Concrete Encasing
5.7.1 |  | (a) Pipe protection Concrete cover slab (25 MPa) accross roadways where indicated by engineer, inclusive of Ref 395 mesh as per eThekwini Standard Details | m³ | 80
TOTAL OF SCHEDULE 5 CARRIED FORWARD TO SUMMARY
| SANS 1200 LB | SCHEDULE 6: BEDDING (PIPES)
6.1 | 8.2.1 & PS LB 3.1 | Provision of Bedding from Trench Excavation
6.1.1 | 8.2.1 (a) | Selected granular material | m³ | 7529.8
6.1.2 | 8.2.1 (b) | Selected fill material | m³ | 5491.8
6.2 | 8.2.2.2 | Bedding from Borrow Pits
6.2.1 | 8.2.2.2 (a) | Selected granular material | m³ | 1882.45
6.2.2 | 8.2.2.2 (b) | Selected fill material | m³ | 1372.95
6.3 | 8.2.2.3 | Imported from commercial source (including haul).
6.3.1 | 8.2.2.3 (a) | Selected granular material | m³ | 470.6
6.3.2 | 8.2.2.3 (b) | Selected fill material | m³ | 343.2
TOTAL OF SCHEDULE 6 CARRIED FORWARD TO SUMMARY
SCHEDULE 7: VALVES AND CHAMBERS
| 8.2.3 | Extra-over 8.2.1 for the supplying, fixing and Bedding of Valves as indicated below:
Isolation Valves Complete
7.1 | PSL 3.13.2 | Supply and install the following flanged Resilient seal Gate valves complete with valve chamber, PN 12 with non-rising spindle, Clockwise closing, including all gaskets, bolts, nuts and washers as per detailed drawings. All valve chambers will be installed by SMME contractors
7.1.1 |  | 50mm | No. | 0 |  | Rate Only
7.1.2 |  | 75mm | No. | 2
7.1.3 |  | 100mm | No. | 2
7.1.4 |  | 150mm | No. | 3
7.1.5 |  | 200mm | No. | 0 |  | Rate Only
Check / Non Return Valves Complete
7.4 | 8.2.5 | Supply and install Check / Non Return Valve assemblies complete with preacast chamber as per detailed drawings. Rate is inclusive of valve chamber and all specials. All valve chambers will be installed by SMME contractors
7.4.1 |  | 200mm | No. | 0 |  | Rate Only
Bulk Water Meter Complete
7.5 | 8.2.5 | Supply and install Bulk Water Meter assemblies complete with protective meter chamber as per detailed drawings. Note: All valve chambers will be installed by SMME contractors
7.5.1 |  | 200mm | No. | 2
7.6 |  | Fire Hydrants
7.6.1 |  | (a) Supply and install cast iron underground-type fire hydrant conforming to SANS 1128, complete with cast iron/polymer cover and frame. 80mm Isolating valve and 100mm x 80mm dia. reducer measured elsewhere. | No. | 4
TOTAL OF SCHEDULE 7 CARRIED FORWARD TO SUMMARY
SCHEDULE 8: GABIONS
8.1 | SABS 1200DK | Gabion/Reno mattresses, using 6x8 mesh with 1,0m diaphragm spacing, of sizes
8.1.1 | 8.2.2 | 2,0 x 2,0 x 0,17m | m³ | 15
8.1.2 |  | 2,0 x 1,0 x 1,0m | m³ | 15
8.2 | PSDK5 | Excavation and compaction in all classes of materials | m³ | 8
8.3 |  | Surface preparation for bedding the gabions | m² | 100
8.4 | 8.2.4 | Filter fabric Grade 4 geotextile with minimum 2.5kN penetration load and at least 235 l/s/m² through flow (ref. PSDK1) | m² | 105
TOTAL OF SCHEDULE 8 CARRIED FORWARD TO SUMMARY

## Borehole Investigation (hidden)
ITEM | PAYMENT REFERS | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
SCHEDULE 9: SITING, DRILLING, TESTING AND EQUIPPING OF BOREHOLES
9.1 |  | BOREHOLE INVESTIGATIONS
9.1.1 |  | (a) Hydrogeological Investigations. Cost to include, inter alia, feasibility assessments, siting of production boreholes sites and WULA/Borehole Registration. | Prov. Sum | 1 | 50000 | 50000
9.1.2 |  | (b) Overheads, charges & profit on above provisional sum | % | 50000 | 10% | 5000
9.1.3 |  | (c) Topographical Surveys and As-built Drawings | Prov. Sum | 1 | 80000 | 80000
9.1.4 |  | (d) Overheads, charges & profit on above provisional sum | % | 80000 | 10% | 8000
9.1.5 |  | (e) Construct 3 No. Production Boreholes, costs to include borehole drilling, pump testing, water quality testing, installation of 5m3/hr | Prov. Sum | 1 | 1200000 | 1200000
9.1.6 |  | (f) Overheads, charges & profit on above provisional sum | % | 1200000 | 10% | 120000
9.2 |  | SUPPLY AND INSTALLATION OF GENERATOR
9.2.1 |  | (a) Supply and install generator and accessories to run Borehole pump system (Note: specification of Generator will be issued by Engineer) | Prov. Sum | 1 | 300000 | 300000
9.2.2 |  | (b) Overheads, charges & profit on above provisional sum | % | 300000 | 10% | 30000
9.3 |  | SUPPLY AND CONSTRUCTION OF PUMPING MAIN
9.3.1 |  | (a) Design, supply and construct 90 mm diameter 16 bar class uPVC pipes for pumping main, air valves, scour valves and related appurtenances for the production borehole sites (Note: A Separate BoQ, itemising and quantifying items provided under this Sum shall be issued before construction is commenced with and shall form the final basis for payment) | Prov. Sum | 1 | 1000000 | 1000000
9.3.2 |  | (b) Overheads, charges & profit on above provisional sum | % | 1000000 | 10% | 100000
9.4 |  | SUPPLY AND CONSTRUCTION OF PIPELINES
9.4.1 |  | (a) Design, supply and construct reticulation using 12 bar class uPVC pipes for the water reticulation network, communal standpipes, valves, meters and related appurtenances for the production borehole sites (Note: A Separate BoQ, itemising and quantifying items provided under this Sum shall be issued before construction is commenced with and shall form the final basis for payment) | Prov. Sum | 1 | 1000000 | 1000000
9.4.2 |  | (b) Overheads, charges & profit on above provisional sum | % | 1000000 | 10% | 100000
TOTAL OF SCHEDULE F CARRIED FORWARD TO SUMMARY | [5 empty] | 3993000